## Sheet1
Unique (ID) | Compliance Requirement | Evidence collected | Independent Audit Findings and Recommendations | Status - Compliant - Non-compliant - Not triggered
PART A ADMINISTRATIVE CONDITIONS
Obligation to Minimise Harm to the Environment
A1 | In addition to meeting the specific performance measures and criteria in this consent, all reasonable and feasible measures must be implemented to prevent, and, if prevention is not reasonable and feasible, minimise any material harm to the environment that may result from the construction and operation of the development. | Information as recorded in this compliance Audit table | RCC were able to demonstrate the implementation of the controls identified in the CEMP and associated sub-plans, as is noted in this compliance table. Control systems inspected on site were found to be in accordance with the undertakings of the sub-plans. Induction processes and tool box talks are used to inform project personnel of requirements Weekly inspections are used to confirm implementation of measures. | Compliant
Terms of Consent
A2 | The development may only be carried out: (a) in compliance with the conditions of this consent; (b) in accordance with all written directions of the Planning Secretary; (c) generally in accordance with the EIS and Response to Submissions; (d) in accordance with the approved plans in the table below: | Conduct of site inspection and review of documentation as outlined in the Independent Audit report and summarised in this Audit Table | This audit confirmed consent conditions are generally being complied with, and in accordance with the EIS and response to submissions. There is evidence that the approved plans have been implemented, as noted in this report RCC advised plans remain unchanged from the previous audit. Additional works on site (DDA access) covered by separate REF and do not form part of the SSDA | Compliant
A3 | Consistent with the requirements in this consent, the Planning Secretary may make written directions to the Applicant in relation to: (a) the content of any strategy, study, system, plan, program, review, audit, notification, report or correspondence submitted under or otherwise made in relation to this consent, including those that are required to be, and have been, approved by the Planning Secretary; (b) any reports, reviews or audits commissioned by the Department regarding compliance with this approval; and (c) the implementation of any actions or measures contained in any such document referred to in (a) above. |  | RCC advised no directions have been issued by the Planning Secretary since the commencement of works on site | Not triggered
A4 | The conditions of this consent and directions of the Planning Secretary prevail to the extent of any inconsistency, ambiguity or conflict between them and a document listed in condition A2(c) or A2(d). In the event of an inconsistency, ambiguity or conflict between any of the documents listed in condition A2(c)A2(c) and A2(d), the most recent document prevails to the extent of the inconsistency, ambiguity or conflict. |  | No inconsistency, ambiguity or conflicts have been identified | Compliant
Limits of Consent
A5 | This consent lapses five years after the date of consent unless the development has physically commenced. |  | N/A - construction commenced November 2019 | Not triggered
Prescribed Conditions
A6 | The Applicant must comply with all relevant prescribed conditions of development consent under Part 6, Division 8A of the EP&A Regulation. | Part 6, Division 8A of the EP&A Regulations relates to prescribed conditions for Compliance with the BCA (cl 98) - Subject land: Lot 4 DP1248441, 664 Pacific Highway Hamlyn Terrace NSW 2259 Crown Certificates No CRO-18164 (CC1) dated 27/11/2019 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) Crown Certificates No CRO-20112 (CC3) dated 21/09/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) | CC3 issued for fit out phase Crown Certificate CC1, CC2 and CC3 confirm requirements have been addressed | Compliant
Planning Secretary as Moderator
A7 | In the event of a dispute between the Applicant and a public authority, in relation to an applicable requirement in this approval or relevant matter relating to the Development, either party may refer the matter to the Planning Secretary for resolution. The Planning Secretary’s resolution of the matter must be binding on the parties. |  | RCC advised there have been no disputes | Not triggered
Evidence of Consultation
A8 | Where conditions of this consent require consultation with an identified party, the Applicant must: (a) consult with the relevant party prior to submitting the subject document for information or approval; and (b) provide details of the consultation undertaken including: (i) the outcome of that consultation, matters resolved and unresolved; and (ii) details of any disagreement remaining between the party consulted and the Applicant and how the Applicant has addressed the matters not resolved. | RCC have created a folder for consultation with "Authorities", which includes Consultation undertaken precommencement of construction: - submission of stormwater plan to council for S138 Certificate - Revision of access at Gate 1 in response to Council Review Note (dated 20/11/2019) - RMS TMC notified, TMP submitted - Consultation with Hospital through Colliers, with weekly meetings - Disruption notice system initiated with Hospital Engineering Department - Fire Brigade have been on site to review bushfire clearing areas - Communication with CASA regarding crane on site (for both hospital helicopter access as well as Warnervale Airport) - Meeting with Council regarding works on Louisiana Road (23 March), plus on site meeting 22/06/2020 to discuss proposed works - Consultation with Fire Rescue NSW (by Health Infrastructure) | RCC advised there have been no disagreements identified | Compliant
Staging
A9 | The project may be constructed and operated in stages. Where staged construction or operation is proposed, a Staging Report (for either or both construction and operation as the case may be) must be prepared and submitted for the approval of the Planning Secretary. The Staging Report must be submitted to the Planning Secretary no later than one month before the commencement of construction of the first of the proposed stages of construction (or if only staged operation is proposed, one month before the commencement of operation of the first of the proposed stages of operation). |  | RCC advised Staging is not required | Not triggered
A10 | A Staging Report prepared in accordance with condition A9 must: (a) if staged construction is proposed, set out how the construction of the whole of the project will be staged, including details of work and other activities to be carried out in each stage and the general timing of when construction of each stage will commence and finish; (b) if staged operation is proposed, set out how the operation of the whole of the project will be staged, including details of work and other activities to be carried out in each stage and the general timing of when operation of each stage will commence and finish (if relevant); (c) specify how compliance with conditions will be achieved across and between each of the stages of the project; and (d) set out mechanisms for managing any cumulative impacts arising from the proposed staging. |  | RCC advised Staging is not required | Not triggered
A11 | Where staging is proposed, the project must be staged in accordance with the Staging Report, as approved by the Planning Secretary. |  | RCC advised Staging is not required | Not triggered
A12 | Where staging is proposed, the terms of this approval that apply or are relevant to the works or activities to be carried out in a specific stage must be complied with at the relevant time for that stage. |  | RCC advised Staging is not required | Not triggered
Staging, Combining and Updating Strategies, Plans or Programs
A13 | With the approval of the Planning Secretary, the Applicant may: (a) prepare and submit any strategy, plan (including management plan, architectural or design plan, compliance reports or independent audits) or program required by this consent on a staged basis (if a clear description is provided as to the specific stage and scope of the development to which the strategy, plan (including management plan, architectural or design plan) or program applies, the relationship of the stage to any future stages and the trigger for updating the strategy, plan (including management plan, architectural or design plan), compliance reports or independent audits or program); (b) combine any strategy, plan (including management plan, architectural or design plan, compliance reports or independent audits), or program required by this consent (if a clear relationship is demonstrated between the strategies, plans (including management plan, architectural or design plan, compliance reports or independent audits) or programs that are proposed to be combined); and (c) update any strategy, plan (including management plan, architectural or design plan, compliance reports or independent audits), or program required by this consent (to ensure the strategies, plans (including management plan, architectural or design plan, compliance reports or independent audits ), or programs required under this consent are updated on a regular basis and incorporate additional measures or amendments to improve the environmental performance of the development). |  | RCC advised Staging is not required | Not triggered
A14 | If the Planning Secretary agrees, a strategy, plan (including management plan, architectural or design plan compliance reports or independent audits), or program may be staged or updated without consultation being undertaken with all parties required to be consulted in the relevant condition in this consent. |  | RCC advised Staging is not required | Not triggered
A15 | If approved by the Planning Secretary, updated strategies, plans (including management plan, architectural or design plan compliance reports or independent audits), or programs supersede the previous versions of them and must be implemented in accordance with the condition that requires the strategy, plan, program or drawing. |  | RCC advised Staging is not required | Not triggered
Demolition
A16 | Demolition work must comply with Australian Standard AS 2601-2001 The Demolition of structures (Standards Australia, 2001). The work plans required by AS 2601-2001 must be accompanied by a written statement from a suitably qualified person that the proposal contained in the work plan comply with the safety requirements of the Standard. The work plans and the statement of compliance must be submitted to the Certifying Authority before the commencement of works. |  | RCC advised no demolition is required for the development works - bridge structure connecting to new facility will be supported external to the existing structure. Works required for connection of bridge into existing structure will be the removal of facia panel and making good into new structure - this is covered by a separate REF and does not form part of these approval conditions. RCC note detailed procedures developed for this work due t infection control requirements for interface with the working hospital | Not triggered
Structural Adequacy
A17 | All new buildings and structures, and any alterations or additions to existing buildings and structures, that are part of the development, must be constructed in accordance with the relevant requirements of the BCA and NCC. | Crown Certificate - CRO-18164 from Certifying Authority dated 27/11/2019, included Structural Design Statement from Structural Engineer (TTW dated 31.10.19) RCC note additional DDA access works are covered by a seperate REF and do not form part of the SSDA |  | Compliant
Note: Part 8 of the EP&A Regulation sets out the requirements for the certification of the development.
External Walls and Cladding
A18 | The external walls of all buildings including additions to existing buildings must comply with the relevant requirements of the BCA and NCC. | RCC noted that Correspondence provided to the Certifying Authority 'RCC-GCOR-000698 B4 DPIE Submission to BM+G and DPIE in relation to B4 - 191203 B4 External Walls DPIE Acceptance Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) Email 24/03/2020 regarding Certifier accepted of the provided facade information Statement dated 11/09/2020 reconfirmed the use of a different supplier (same product specification) | CC2 issued 25/03/2020 RCC proposing to use Kingspan Aluminium Panels - accepted by Crown Certifier Subsequent statement issued nominating alternative suppliers (material specification remains unchanged) | Compliant
Applicability of Guidelines
A19 | References in the conditions of this consent to any guideline, protocol, Australian Standard or policy are to such guidelines, protocols, Standards or policies in the form they are in as at the date of this consent. |  | RCC advised that there have been no directions received by Planning Secretary to comply with updated or revised guidelines, protocols, Standards or policies. | Not triggered
A20 | Consistent with the conditions of this consent and without altering any limits or criteria in this consent, the Planning Secretary may, when issuing directions under this consent in respect of ongoing monitoring and management obligations, require compliance with an updated or revised version of such a guideline, protocol, Standard or policy, or a replacement of them. |  | RCC advised that there have been no directions received by Planning Secretary to comply with updated or revised guidelines, protocols, Standards or policies. | Not triggered
Monitoring and Environmental Audits
A21 | Any condition of this consent that requires the carrying out of monitoring or an environmental audit, whether directly or by way of a plan, strategy or program, is taken to be a condition requiring monitoring or an environmental audit under Division 9.4 of Part 9 of the EP&A Act. This includes conditions in respect of incident notification, reporting and response, non-compliance notification, Site audit report and independent auditing. Note: For the purposes of this condition, as set out in the EP&A Act, “monitoring” is monitoring of the development to provide data on compliance with the consent or on the environmental impact of the development, and an “environmental audit” is a periodic or particular documented evaluation of the development to provide information on compliance with the consent or the environmental management or impact of the development. |  | RCC advised that this requirement had not been triggered at the time of this audit | Not triggered
Access to Information
A22 | At least 48 hours before the commencement of construction until the completion of all works under this consent, or such other time as agreed by the Planning Secretary, the Applicant must: (a) make the following information and documents (as they are obtained or approved) publicly available on its website: (i) the documents referred to in condition A2 of this consent; (ii) all current statutory approvals for the development; (iii) all approved strategies, plans and programs required under the conditions of this consent; (iv) regular reporting on the environmental performance of the development in accordance with the reporting arrangements in any plans or programs approved under the conditions of this consent; (v) a comprehensive summary of the monitoring results of the development, reported in accordance with the specifications in any conditions of this consent, or any approved plans and programs; (vi) a summary of the current stage and progress of the development; (vii) contact details to enquire about the development or to make a complaint; (viii) a complaints register, updated monthly; (ix) audit reports prepared as part of any independent audit of the development and the Applicant’s response to the recommendations in any audit report; (x) any other matter required by the Planning Secretary; and (b) keep such information up to date, to the satisfaction of the Planning Secretary | Review of Project website http://www.gwhr.health.nsw.gov.au/wyong-hospital-redevelopment confirmed the following have been made available: 1) Environmental Impact Statement 2) SSD 9536 Notice of Assessment 3) SSD 9536 Development Consent 4) SSD 9536 Assessment Report 5) SSD 9536 Approved Plans 6) Compliance Monitoring Reporting Program 7) Pre-construction Compliance Monitoring Program 8) Complaints Register - dated August 2020 9) Independent Audit Program 10) Independent Audit 1 11) Independent Audit Report - Number 1 12) Dilapidation Reports (Property Condition surveys for Louisiana Road, Wyong Hospital Carpark, Louisiana House) 13) Construction Environmental Management Plan 14) Construction Traffic and Pedestrian Management Sub-Plan 15) Aboriginal Cultural Heritage Management Sub-Plan | It is noted that the CEMP does not identify any reporting requirements for the development Health Infrastructure will upload information received from RCC | Compliant
Compliance
A23 | The Applicant must ensure that all of its employees, contractors (and their sub-contractors) are made aware of, and are instructed to comply with, the conditions of this consent relevant to activities they carry out in respect of the development. | Review of contract documents confirmed SSDA requirements reflected in the contract condition Sighted Site Toolbox talks which include relevant information, including deliveries, environmental controls, fuel and chemical storage, dust control and the preservation of designated trees Toolbox talks also completed in response to previous audit findings Sighted emails instructing delivery drivers on protocols for attendance on site | No change to information process. RCC will inform Supervisor of current access arrangement, Supervisor informs sub-contractors. Delivery to site for next day discussed at daily planning meeting involving RCC and all subcontractors | Compliant
Incident Notification, Reporting and Response
A24 | The Department must be notified in writing to compliance@planning.nsw.gov.au immediately after the Applicant becomes aware of an incident. The notification must identify the development (including the development application number and the name of the development if it has one), and set out the location and nature of the incident. |  | RCC advised that there have been no environmental incidents | Not triggered
A25 | Subsequent notification must be given and reports submitted in accordance with the requirements set out in Appendix 1. |  | RCC advised that there have been no environmental incidents | Not triggered
Non-Compliance Notification
A26 | The Department must be notified in writing to compliance@planning.nsw.gov.au within seven days after the Applicant becomes aware of any non-compliance. The Certifying Authority must also notify the Department in writing to compliance@planning.nsw.gov.au within seven days after they identify any non-compliance. |  | RCC advised no non-compliances have been identified in the period since the previous Audit Report was issued | Not triggered
A27 | The notification must identify the development and the application number for it, set out the condition of consent that the development is non-compliant with, the way in which it does not comply and the reasons for the non-compliance (if known) and what actions have been, or will be, undertaken to address the non-compliance |  | RCC advised no non-compliances have been identified in the period since the Pre-construction compliance report was issued | Not triggered
A28 | A non-compliance which has been notified as an incident does not need to also be notified as a non-compliance |  | RCC advised no non-compliances have been identified in the period since the initial site audit report was issued | Not triggered
Revision of Strategies, Plans and Programs
A29 | Within three months of: (a) the submission of a compliance report under condition B29; (b) the submission of an incident report under condition A24; (c) the submission of an Independent Audit under condition C32; (d) the approval of any modification of the conditions of this consent; or (e) the issue of a direction of the Planning Secretary under condition A2 which requires a review, the strategies, plans and programs required under this consent must be reviewed, and the Department and the Principal Certifying Authority must be notified in writing that a review is being carried out. |  | RCC advised that there has been no requirement to undertake a review of the strategies, plans and programs required under this consent B29 Compliance report issued in April - 3 month timeframe has not been exceeded Project Plan will be reviewed review at different stages of construction (last was in July 2020) - may include consideration of environmental plans, if required (nil to date) | Not triggered
A30 | If necessary to either improve the environmental performance of the development, cater for a modification or comply with a direction, the strategies, plans and programs required under this consent must be revised, to the satisfaction of the Certifying Authority. Where revisions are required, the revised document must be submitted to the Certifying Authority for approval within six weeks of the review. Note: This is to ensure strategies, plans and programs are updated on a regular basis and to incorporate any recommended measures to improve the environmental performance of the development. |  | Next review scheduled for December 2020 | Not triggered
PART B PRIOR TO COMMENCEMENT OF CONSTRUCTION
Notification of Commencement
B1 | The Applicant must notify the Department in writing of the dates of commencement of physical work and operation at least 48 hours before those dates. | Sighted Crown Certificate - CRO-18164 FROM Certifying Authority RCC presented letter dated 25 November 2019 from RCC to NSW Department of Planning and Certifying Authority notifying of commencement of construction on 28 November 2019 | CC3 issued for fit out - no change to project requirements | Compliant
B2 | If the construction or operation of the development is to be staged, the Department must be notified in writing at least 48 hours before the commencement of each stage, of the date of commencement and the development to be carried out in that stage. |  | RCC advised Staging is not required | Not triggered
Certified Drawings
B3 | Prior to the commencement of construction, the Applicant must submit to the satisfaction of the Certifying Authority structural drawings prepared and signed by a suitably qualified practising Structural Engineer | TTW issued certificate for issue of drawings to Certifying Authority Crown Certificate - CRO-18164 FROM Certifying Authority General Arrangement drawings on Web Site for CC1 CC2 refers to Structural Design Certificate dated 4 February 2020 | Design compliant for current project activities - No change to structural drawings | Compliant
External Walls and Cladding
B4 | Prior to the commencement of construction, the Applicant must provide the Certifying Authority with documented evidence that the products and systems proposed for use or used in the construction of external walls, including finishes and claddings such as synthetic or aluminium composite panels, comply with the requirements of the BCA. The Applicant must provide a copy of the documentation given to the Certifying Authority to the Planning Secretary within seven days after the Certifying Authority accepts it. | Wall system certificate dated 20/11/2019 RCC emailed to Certifying Authority 25/11/2019 (RCC-GCOR-000638) The certifying authority confirmed compliance of submitted documentation in accordance with this requirement on 25/11/19 BM+G-GCOR-000085. Certifying Authority Acceptance provided to DPIE on 28/11/2019 - by HI Planning DPIE accepted Certifying Authorities approval and documentation on 03/12/2019. RCC noted that Correspondence provided to the Certifying Authority 'RCC-GCOR-000698 B4 DPIE Submission to BM+G and DPIE in relation to B4 - 191203 B4 External Walls DPIE Acceptance Confirmation of acceptance received in email: Fw:Wyong Hospital Expansion - External Cladding on 03/12/2019 Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) Email 24/03/2020 regarding Certifier accepted of the provided facade information Statement dated 11/09/2020 confirmed the use of a different supplier (same product specification) | RCC advised information submitted through DPIE submission portal by HI Planning. CC2 issued 25/03/2020 RCC proposing to use Kingspan Aluminium Panels - accepted by Crown Certifier RCC advised there has been a change in sarking supplier - no change in specification of the product Using Speed panel on the Link Bridge - subsequent statement issued nominating alternative suppliers (material specification remains unchanged) | Compliant
Road Design
B5 | Prior to the commencement of above ground works, (a) a Detailed Design Road Safety Audit (RSA) for the proposed development’s including its interaction with the existing hospital campus as well as the intersection to the new access road with Louisiana Road prepared by a minimum Level 3 & Level 2 TfNSW accredited road safety auditor. (b) should findings of the RSA identify any road safety issues that require rectification , the detailed design drawings must be revised accordingly to resolve the identified safety issues. A copy of the RSA and any revised plans is to be provided to the Certifying Authority, Council and the Planning Secretary for information. | Submission to Council of TTW 191125 Detailed Design Road Safety Audit with Responses' sent and receipt received in correspondence RE: RE: SSD9536 - Wyong Hospital Refurbishment - B5 - Road Safety Audit. | RCC stated that Identified Issues are to do with Wayfinding, and will be addressed with the CC4 submission in December 2020 RCC noted signage and wayfaring is campus wide, pat of CC$, and will ne installed before pre-occupancy phase commences RCC advised that nil response received from Council to date. | Compliant
Protection of Public Infrastructure
B6 | Prior to the commencement of construction, the Applicant must: (a) consult with the relevant owner and provider of services/ assets that are likely to be affected by the development to make suitable arrangements for access to, diversion, protection and support of the affected infrastructure; (b) prepare a dilapidation report identifying the condition of all public infrastructure in the vicinity of the site (including roads, gutters and footpaths); and (c) submit a copy of the dilapidation report to the Planning Secretary and Certifying Authority and Council. | Dilapidation reports (by AusDilaps, dated 05/11/2019) undertaken for Louisiana Road, Louisiana House and Hospital grounds - posted on web site The dilapidation report was issued to certifying authority and council: 1) CM SSD9536 - Condition B6 - Protection of Public Infrastructure - Dated 11 November 2019. 2) Notification to Council : RCC-GCOR-000431 - 14 November 2019. Sighted Council Acceptance of Dilapidation Report Received 14 November 2019 Submission and Notification to DPIE - 15 November 2019 by HI Planning Portal | RCC note existing sewer not impacted by development - line of sewer identified on site by flagging Ongoing liaison with Council on site to review relocation works and for cut over of supply lines - existing water supply line rerouted as part of this development | Compliant
Site Contamination
B7 | Upon completion of remedial works, the Applicant must submit a Site Audit Report and Section A Site Audit Statement for the relevant part of the site prepared by a EPA accredited Site Auditor. The Site Audit Report and Section A Site Audit Statement must verify the relevant part of the site is suitable for the healthcare facility land use and be provided to the satisfaction of the Certifying Authority | RCC presented GHD Site Audit Report 0086_DG October 2019 NSW EPA Site Audit Statement dated 21 October 2019 - advising the suitability of site for healthcare facility |  | Compliant
Unexpected Contamination Procedure
B8 | Prior to the commencement of earthworks, the Applicant must prepare an unexpected contamination procedure to ensure that potentially contaminated material is appropriately managed. The procedure must form part of the of the CEMP in accordance with condition B1812 and where any material identified as contaminated is to be disposed off-site, the disposal location and results of testing submitted to the Planning Secretary prior to its removal from the site. | Attachment F to CEMP - Asbestos and Unexpected Contamination Management Plan dated October 2019 RCC presented Asbestos Identification Report dated 4/11/19 from ama Monitoring Services - no asbestos noted RCC presented Asbestos Identification Report dated 08/10/2020 regarding contamination in material stockpile behind Nursing Home on adjacent land | Relocation of water service has included removal of ACM Pipe - RCC in process of confirming process used for the disposal of the pipe identified through project planning process | Compliant
Ecologically Sustainable Development
B9 | Prior to the commencement of any aboveground work, unless otherwise agreed by the Planning Secretary, the Applicant must demonstrate that ESD is being achieved by either: (a) registering for a minimum 4 star Green Star rating with the Green Building Council of Australia and submit evidence of registration to the Certifying Authority; or (b) seeking approval from the Planning Secretary for an alternative certification process. | Planning secretary letter (dated 22/11/2019) received confirming acceptance of the use of the HI ESD matrix and framework | RCC believe they will achieve 50 points (45 is minimum allowable) Gateway1 submission targeted for end November 2020. Gateway 2 (Validation & Commissioning) scheduled for end March 2021 | Compliant
Outdoor Lighting
B10 | Prior to commencement of lighting installation, evidence must be submitted to the satisfaction of the Certifying Authority that all outdoor lighting within the site has been designed to comply with AS 1158.3.1:2005 Lighting for roads and public spaces – Pedestrian area (Category P) lighting – Performance and design requirements and AS 4282-2019 Control of the obtrusive effects of outdoor lighting. | Electrical lighting plan and outdoor lighting design to be provided by electrical consultant with certification confirming compliance to AS 1158.3.1:2005 Lighting for Roads and Public Spaces - Pedestrian (Category P) Lighting Performance and design documentation along with certification to be provided confirming compliance to AS 4282-2019 Control of Obtrusive Effects of Outdoor Lighting. CC2 includes reference to Certificate of Design Intent - Electrical (Outdoor Lighting) by LEHR Consultants International dated 24/01/2020 | RCC advised no change to design Requirement addressed | Compliant
Environmental Management Plan Requirements
B11 | Management plans required under this consent must be prepared in accordance with relevant guidelines, and include: (a) detailed baseline data; (b) details of: (i) the relevant statutory requirements (including any relevant approval, licence or lease conditions); (ii) any relevant limits or performance measures and criteria; and (iii) the specific performance indicators that are proposed to be used to judge the performance of, or guide the implementation of, the development or any management measures; (c) a description of the measures to be implemented to comply with the relevant statutory requirements, limits, or performance measures and criteria; (d) a program to monitor and report on the: (i) impacts and environmental performance of the development; (ii) effectiveness of the management measures set out pursuant to paragraph (c) above; (e) a contingency plan to manage any unpredicted impacts and their consequences and to ensure that ongoing impacts reduce to levels below relevant impact assessment criteria as quickly as possible; (f) a program to investigate and implement ways to improve the environmental performance of the development over time; (g) a protocol for managing and reporting any: (i) incident and any non-compliance (specifically including any exceedance of the impact assessment criteria and performance criteria); (ii) complaint; (iii) failure to comply with statutory requirements; and (h) a protocol for periodic review / update of the plan and any updates in response to incidents or matters of non-compliance. Note: The Planning Secretary may waive some of these requirements if they are unnecessary or unwarranted for particular management plans | CEMP, EMP and Sub-plans provided to Certifying Authority and confirmed in Crown Certificate CRO-18164 dated 27 November 2019. Environmental audit conducted 16 July 2020 Presented evidence of environmental inspection after rain (8 August, 14 August, 29 August, 25 November) | RCC identified the following processes to overview EMP implementation 1) Weekly site inspections of environmental controls 2) Inspections after major rain events 3) Monthly report includes noise and dust monitoring results 4) HI feedback 5) RCC audits of management plan implementation (Note April 2020 audit postponed due to Covid-19, rescheduled for July) 6) The site may be included in external Certification of Management Systems (nil to date) | Compliant
Construction Environmental Management Plan
B12 | Prior to the commencement of construction, the Applicant must submit a Construction Environmental Management Plan (CEMP) to the satisfaction of Certifying Authority and provide a copy to the Planning Secretary. The CEMP must include, but not be limited to, the following: (a) Details of: (i) hours of work; (ii) 24-hour contact details of site manager; (iii) management of dust and odour to protect the amenity of the neighbourhood; (iv) stormwater control and discharge; (v) measures to ensure that sediment and other materials are not tracked onto the roadway by vehicles leaving the site; (vi) groundwater management plan including measures to prevent groundwater contamination; (vii) external lighting in compliance with AS 4282-2019 Control of the obtrusive effects of outdoor lighting; (viii) community consultation and complaints handling; (b) Construction Traffic and Pedestrian Management Sub-Plan (see condition B19); (c) Construction Noise and Vibration Management Sub-Plan (see condition B20); (d) Construction Waste Management Sub-Plan (see condition B21); (e) Construction Soil and Water Management Sub-Plan (see condition B22); (f) Aboriginal Cultural Heritage Management Sub-Plan (see condition B23); (g) Biodiversity Management Sub-Plan (see condition B24); (h) an unexpected finds protocol for contamination and associated communications procedure; (i) an unexpected finds protocol for Aboriginal and non-Aboriginal heritage and associated communications procedure; (j) waste classification (for materials to be removed) and validation (for materials to remain) be undertaken to confirm the contamination status in these areas of the site; and | CEMP presented is Rev 1 dated 22/11/19 CEMP prepared by Travers Bushfire and Ecology (a) CEMP includes relevant details of: (i) hours of work [CEMP 4.6]; (ii) 24-hour contact details of site manager [CEMP 8.5]; (iii) management of dust and odour to protect the amenity of the neighbourhood [CEMP 6.1.9]; (iv) stormwater control and discharge [CEMP 6.1.3, Attachment E]; (v) measures to ensure that sediment and other materials are not tracked onto the roadway by vehicles leaving the site [CEMP 6.1.3, Attachment E]; (vi) groundwater management plan including measures to prevent groundwater contamination [CEMP 6.1.3, Attachment E]; (vii) external lighting in compliance with AS 4282-2019 Control of the obtrusive effects of outdoor lighting [CEMP 3.2]; (viii) community consultation and complaints handling [CEMP 8.4]; (b) Construction Traffic and Pedestrian Management Sub-Plan (see condition B19) [CEMP Attachment B]; (c) Construction Noise and Vibration Management Sub-Plan (see condition B20)[CEMP Attachment C]; (d) Construction Waste Management Sub-Plan (see condition B21)[CEMP Attachment D]; (e) Construction Soil and Water Management Sub-Plan (see condition B22)[CEMP Attachment E]; (f) Aboriginal Cultural Heritage Management Sub-Plan (see condition B23)[CEMP 6.1.7 plus separate plan]; (g) Biodiversity Management Sub-Plan (see condition B24)[CEMP Attachment H]; (h) an unexpected finds protocol for contamination and associated communications procedure [CEMP 6.1.2]; (i) an unexpected finds protocol for Aboriginal and non-Aboriginal heritage and associated communications procedure [CEMP 6.1.7]; (j) waste classification (for materials to be removed) and validation (for materials to remain) be undertaken to confirm the contamination status in these areas of the site [CEMP 6.1.12]; | CEMP is a comprehensive document that addresses SSDA 9536 - no change to document | Compliant
B13 | The Construction Traffic and Pedestrian Management Sub-Plan (CTPMSP) must address, but not be limited to, the following: (a) be prepared by a suitably qualified and experienced person(s); (b) be prepared in consultation with Council and TfNSW(RMS); (c) detail the measures that are to be implemented to ensure road safety and network efficiency during construction in consideration of potential impacts on general traffic, cyclists and pedestrians and bus services; (d) detail heavy vehicle routes, access and parking arrangements; (e) include a Driver Code of Conduct to: (i) minimise the impacts of earthworks and construction on the local and regional road network; (ii) minimise conflicts with other road users; (iii) minimise road traffic noise; and (iv) ensure truck drivers use specified routes; (f) include a program to monitor the effectiveness of these measures; and (g) if necessary, detail procedures for notifying residents and the community (including local schools), of any potential disruptions to routes. | The original CTPMSP (dated 14/11/2019) was prepared by TTW to comply with B13 Plan has been submitted to Council RCC noted that the Plan has been updated - now 7 January 2020 - change due to Traffic Control Plan being modified to reflect one traffic controller on site during normal operations RCC Presented Traffic Control Plan TCP 657 dated 18/10/2020 for revised access point at Louisiana Road RCC presented instruction for deliveries to the project site (issued to all organisations transporting material to or from the construction site) | Traffic control measures identified in the plan were demonstrated during this audit, including heavy vehicle delivery routes A Drivers Code of conduct is included in Section 4.5 of the CTPMSP, monitoring through tight control of deliveries through front gate - any vehicle arriving without appropriate notification will be sent away Notification protocols have been established and were demonstrated during this audit. Any deliveries with the potential to disrupt would be communicated through this proven system | Compliant
B14 | The Construction Noise and Vibration Management Sub-Plan must address, but not be limited to, the following: (a) be prepared by a suitably qualified and experienced noise expert; (b) describe procedures for achieving the noise management levels in EPA’s Interim Construction Noise Guideline (DECC, 2009); (c) describe the measures to be implemented to manage high noise generating works such as piling, in close proximity to sensitive receivers; (d) include strategies that have been developed with the community for managing high noise generating works; (e) describe the community consultation undertaken to develop the strategies in condition B20(d); and (f) include a complaints management system that would be implemented for the duration of the construction. | Noise and Vibration Management Plan (Version 1, dated 24/10/2019) was prepared by Greencap (Acoustic Consultant), and includes processes to achieve the EPS's Interim Construction Noise Guideline The plan includes strategies for managing high noise generating works [NVMP 5.3] Section 6.6 of the NVMP outlines the community consultation undertaken A complaints register has been established - copy included on the project web site Presented Noise and Vibration Report for July, dated 5/08/2020 | RCC stated that they do not intend to use high noise generating works such as percussive piling or rock breaking on site, however hours of work for these activities are identified with appropriate respite periods - there has been nil requirement for this to date Monitoring points have been established on site - Greencap will advise RCC when there is an exceedance (real time measuring)) A complaints register has been established Noise and vibration levels reports included in monthly project report prepared by RCC- nil exceedances noted Monitoring ceased in August with the completion of noisy works (following completion of bridge installation) | Compliant
B15 | The Construction Waste Management Sub-Plan (CWMSP) must address, but not be limited to, the following: (a) detail the quantities of each waste type generated during construction and the proposed reuse, recycling and disposal locations; (b) removal of hazardous materials, particularly the method of containment and control of emission of fibres to the air, and disposal at an approved waste disposal facility in accordance with the requirements of the relevant legislation, codes, standards and guidelines, prior to the commencement of any building works. | Presented Construction Waste Sub Plan dated 10/10/2019 Presented Summary of Waste for project dated October 2020 | Plan developed around RCC company wide initiative for waste minimisation, with a target of 80% of waste to be recycled - monthly waste report generated and issued to RCC Senior Management Actual result on site is 93%, and outcomes included in monthly reports Operational controls and method of recording/reporting is defined Waste quantity estimate guideline included Unexpected finds procedure includes protocol for managing hazardous material | Compliant
B16 | The Applicant must prepare a Construction Soil and Water Management Plan (CSWMSP) and the plan must address, but not be limited to the following: (a) be prepared by a suitably qualified expert, in consultation with Council; (b) describe all erosion and sediment controls to be implemented during construction; (c) provide a plan of how all construction works will be managed in a wet-weather events (i.e. storage of equipment, stabilisation of the Site); (d) detail all off-Site flows from the Site; and (e) describe the measures that must be implemented to manage stormwater and flood flows for small and large sized events, including, but not limited to 1 in 1-year ARI, 1 in 5-year ARI and 1 in 100-year ARI). | Presented CSWMP, dated 08/11/2019, prepared by TTW Erosion and Sedimentation control plans have been initiated on site Sedimentation basin size calculations are included in plan Inclement weather procedure included in plan RCC undertake weekly inspections, and after rain events - sighted inspection reports | System relies on use of bunds to pond water and allow for natural ingress, with sedimentation fence installed at the perimeter Additional sedimentation pond developed There is no evidence of sedimentation flow off site RCC stated that TTW have also attended site to inspect installation of controls | Compliant
B17 | The Aboriginal Cultural Heritage Management Sub-Plan (ACHMSP) must address, but not be limited to, the following: (a) be prepared by a suitably qualified and experienced expert in consultation with the Registered Aboriginal Parties; (b) be submitted to the satisfaction of the Planning Secretary prior to construction of any part of the development. (c) adhere to the recommendations of the report titled Aboriginal Heritage Impact Assessment, dated 25 January 2019, prepared by McCardle Cultural Heritage Pty Ltd. | Presented ACHMP, dated 07/10/2019, prepared by McCardle Cultural Heritage P/L RCC presented Submission to DPIE and Certifying Authority approval Letter DPIE- ACHMSP Approval Letter 191128 | Evidence presented to demonstrate regular inspection of control measures RCC stated there had been 1200mm of rain in 2020, with no uncontrolled discharge from site, and no need to treat and pump water due to nature of soils on the project | Compliant
B18 | The Biodiversity Management Sub-Plan (BMSP) must address, but not be limited to, the following: (a) be prepared by a suitably qualified and experienced ecologist; (b) engagement of an appropriately qualified ecologist with experience in capturing native wildlife to be on site for all vegetation removal activities; (c) clearing protocol; (d) measures to minimise the loss of key fauna habitat, including hollow trees; (e) measures to minimise the impacts on fauna on site, including conducting fauna pre-clearance surveys prior to vegetation clearing; (f) controlling weeds and feral pests; (g) measures to ensure biodiversity values not intended to be impacted are protected, including barriers and mapping of protected/’no-go’ areas; and (h) a program to monitor the effectiveness of the measures in the BMSP. | Presented Biodiversity Management Plan, dated 20/11/2019 Plan provides a detailed response to the requirements of the planning approval Habitat trees identified There was no evidence observed during a site inspection of weeds and feral pests within the works zone | Plan prepared by Travers Bushfire and Ecology RCC stated an ecologist was on site during clearing operations - no further finds identified since previous audit Cleared area still being prepared for rehabilitation RCC are restoring fences to restrict access to cleared zone Monitoring program defined in plan | Compliant
Construction Parking
B19 | Prior to the commencement of construction, the Applicant must provide sufficient parking facilities on-site or other travel arrangements for construction workers, including for heavy vehicles [and for site personnel], to ensure that construction traffic associated with the development does not utilise public and residential streets or public parking facilities. | Parking areas established as set out in the CTMSP it was observed during this audit that the capacity of parking area was approaching exceedance exceeded 15 new parking spaces being established for the hospital car park. RCC have obtained 25 spots in adjacent Medical Centre, and have identified parking area adjacent to recreational area as overflow for work force. Security guard on site until 9AM every work day morning to direct workers to alternative parking areas | Compliant, however there is a need to review this aspect | Compliant
Stormwater Management System
B20 | Prior to the commencement of construction, the Applicant must design an operational stormwater management system for the development and submit it to the satisfaction of the Certifying Authority. The system must: (a) be designed by a suitably qualified and experienced person(s); (b) be generally in accordance with the conceptual design in the EIS; (c) be in accordance with applicable Australian Standards; (d) ensure that the system capacity has been designed in accordance with Australian Rainfall and Runoff (Engineers Australia, 2016) and Managing Urban Stormwater: Council Handbook (EPA, 1997) guidelines; (e) divert existing clean surface water around operational areas of the site; (f) direct all sediment laden water in overland flow away from the leachate management system; and (g) prevent cross-contamination of clean and sediment or leachate laden water. | Operational stormwater management system designed by TTW Certificate of Design - Civil dated 14 November 2019, prepared by Taylor Thomson Whitting. RCC advised that Roads Act Approval, Storm Water Drainage Works & Water Management Act Approval in relation to SCC/102/2019 Certificate of design certifies compliance with: 1) SSDA consent dated 29/08/2019 2) AS1428, AS2890, AS3500 3) Australian Rainfall and Runoff (Engineers Australia, 2016) and Managing Urban Stormwater: Council Handbook (EPA 1997) | Clean water from carpark upstream of site is discharge into existing sedimentation pond below the work area - use natural filtration to disperse water Sediment laden water is retained by bunds and sedimentation fences | Compliant
Operational Noise - Design of Mechanical Plant and Equipment
B21 | Prior to installation of mechanical plant and equipment, the Applicant must incorporate the noise mitigation recommendations in the Wyong Hospital Redevelopment Environmental Impact Statement Report - SSD No 9536 - Acoustic and Vibration Assessment prepared by Pulse Acoustic Consultancy dated 31 January 2019, into the detailed design drawings. The Certifying Authority must verify that all reasonable and feasible noise mitigation measures have been incorporated into the design to ensure the development will not exceed the recommended operational noise levels identified in the Wyong Hospital Redevelopment Environmental Impact Statement Report - SSD No 9536 - Acoustic and Vibration Assessment prepared by Pulse Acoustic Agency Consultancy dated 31 January 2019. | RCC presented the Design Certificate for Mechanical Installation dated 3 August 2020 from LCI | Certificate notes that works are being undertaken on a Design and Construction basis, with Installation Certificates to be provided upon completion of the works | Compliant
Biodiversity
B22 | The SSD application for the Redevelopment of Wyong Hospital must demonstrate that the proposal is consistent with the endorsed Biodiversity Development Assessment Report (BDAR) and Biodiversity Offset Scheme (BOS). | Biodiversity assessment included I BMSP Section 4 of the plan sets out biodiversity impact mitigation works and procedures | Addressed through revised landscaping design, currently negotiating change in scope with HI | Compliant
Construction and Demolition Waste Management
B23 | Prior to the commencement of the removal of any waste material from the site or delivery to the site, the Applicant must notify advise in writing the RMS Traffic Management Centre and Council of the truck route(s) to be followed by trucks transporting waste material from the site. | Correspondence with RMS and Council (RCR2019/004840: Wyong Hospital Development - Main Works CTPMSP - Request for consultation prior to commencement of construction works TTW_181457) | No change this audit | Compliant
Roadworks and Access
B24 | Prior to the commencement of relevant works, the Applicant must submit design plans to the satisfaction of the relevant roads authority which demonstrate that the proposed accesses to the development are designed to accommodate the turning path of construction vehicles. | Correspondence with RMS and Council (RCR2019/004840: Wyong Hospital Development - Main Works CTPMSP - Request for consultation prior to commencement of construction works TTW_181457) |  | Compliant
B25 | Prior to the commencement of relevant works, the Applicant must submit design plans to the satisfaction of the Certifying Authority which demonstrates that the proposed internal roads comply with section 4.2.7 of Planning for Bush Fire Protection 2006. | BFP Statement and Design documentation undertaken by Travers Bushfire & Ecology. RCC note submission to Certifying Authority (GCOR-0005888, 22/11/2019) - no reply received | TTW Design Documentation reflects the outcomes of this assessment. Clear zone established south of the proposed hospital building | Compliant
Operational Car Parking and Service Vehicle Layout
B26 | Prior to the commencement of relevant works, compliance with the following requirements must be submitted to the satisfaction of the Certifying Authority; (a) all construction vehicles must enter and leave the Site in a forward direction; (b) details of on-site car parking spaces for use during operation of the development and designed in accordance with the latest version of AS2890.1, 2 & 6; (c) the swept path of the longest construction vehicle entering and exiting the Site in association with the new work, as well as manoeuvrability through the Site, must be in accordance with the latest version of AS 2890.2; and (d) the safety of vehicles and pedestrians accessing adjoining properties, where shared vehicle and pedestrian access occurs, is to be addressed. | TMP submitted to Certifying Authority (revised plan issued 13/12/2019) - RCC GCOR-000676 15 additional spots constructed appropriate evidence of allowance for pedestrians on site | Site inspection confirmed all vehicles entering and leaving site in a forward direction Swept path indicated on CTPMP Full time traffic controller and gate keeper on main construction access gate (gate 1) | Compliant
Bicycle Parking and End of Trip Facilities
B27 | Prior to the commencement of construction, compliance with the following requirements for secure bicycle parking and end-of-trip facilities must be submitted to the satisfaction of the Certifying Authority: a) the provision of a minimum 12 bicycle parking spaces; b) the layout, design and security of bicycle facilities must comply with the minimum requirements of AS/NZS 2890.3:2015 Parking facilities - Bicycle parking, and be located in easy to access, well-lit areas that incorporate passive surveillance; c) the provision of end-of-trip facilities for staff; d) appropriate pedestrian and cyclist advisory signs are to be provided; and e) all works/regulatory signposting associated with the proposed developments shall be at no cost to the relevant roads authority. | Provided by HDR - GCOR001001, 25/11/2019 (design sketch) | Included in Architectural drawings for CC2 submission | Compliant
Public Domain Works
B28 | Prior to the commencement of any footpath or public domain works (where proposed on Council property), the Applicant must consult with Council and demonstrate to the Certifying Authority that the streetscape design and treatment meets the requirements of Council, including addressing pedestrian management. The Applicant must submit documentation of consultation for each stage from Council to the Certifying Authority. | Addressed in TTW Design Report dated 13/10/2-19 Presented TTW email; to Council dated 1/5/2019 regarding streetscape RCC letter of 25/11/2019 also addresses this issue | Addressed through new entry and associated works in Louisiana Road | Compliant
Compliance Reporting
B29 | No later than two weeks before the date notified for the commencement of construction, a Compliance Monitoring and Reporting Program prepared in accordance with the Compliance Reporting Post Approval Requirements (Department 2018) must be submitted to the Department and the Principal Certifying Authority | Compliance and Monitoring program now prepared and on Project Website | Submitted in April 2020 | Compliant
B30 | The Applicant must make each Compliance Report publicly available 60 days after submitting it to the Department and notify the Department and the Principal Certifying Authority in writing at least seven days before this is done. | Pre-construction Compliance Report has been uploaded to web site Independent Audit reports available on Project Website | Material made available to HI, will be uploaded in the 60 days | Compliant
B31 | Notwithstanding the requirements of the Compliance Reporting Post Approval Requirements (Department 2018), the Planning Secretary may approve a request for ongoing annual operational compliance reports to be ceased, where it has been demonstrated to the Planning Secretary’s satisfaction that an operational compliance report has demonstrated operational compliance |  | RCC advised no directions received | Not triggered
PART C DURING CONSTRUCITON
Site Notice
C1 | A site notice(s): (a) must be prominently displayed at the boundaries of the site during construction for the purposes of informing the public of project details including, but not limited to the details of the Builder, Certifying Authority and Structural Engineer. (b) minimum dimensions of the notice must measure 841 mm x 594 mm (A1) with any text on the notice to be a minimum of 30-point type size; (c) the notice is to be durable and weatherproof and is to be displayed throughout the works period; (d) the approved hours of work, the name of the site/ project manager, the responsible managing company (if any), its address and 24-hour contact phone number for any inquiries, including construction/ noise complaint must be displayed on the site notice; and (e) the notice(s) is to be mounted at eye level on the perimeter hoardings/fencing and is to state that unauthorised entry to the site is not permitted. | Site notice on display at site boundary (at project access points) | Sign was updated immediately following the previous audit to include all required information | Compliant
Operation of Plant and Equipment
C2 | All construction plant and equipment used on site must be maintained in a proper and efficient condition and operated in a proper and efficient manner. | Sub-contractors required to confirmed plant is maintained before arriving on site - plant incoming inspection undertaken by supervisor Plant will be reviewed as part of weekly site inspection There were no obvious signs of poorly maintained equipment observed during the site inspection for this audit | RCC can obtain maintenance records if required | Compliant
Demolition
C3 | Any demolition work must comply with Australian Standard AS 2601-2001 The demolition of structures (Standards Australia, 2001) |  | RCC advised no demolition works proposed for the SDD9536 development | Not triggered
Construction Hours
C4 | Construction, including the delivery of materials to and from the site, may only be carried out between the following hours: (a) between 7am and 6pm, Mondays to Fridays inclusive; and (b) between 8am and 1pm, Saturdays. No work may be carried out on Sundays or public holidays | Hours of work communicated in the CEMP and NVMP as well as the CTPMSP Hours of work included in the project induction RCC note they are allowed to work extended hours - notification received from Minister Planning and Public Spaces dated 31 March 2020 Site is now working 08:00 to 17:00 on Saturdays and 08:00 to 13:00 on Sundays |  | Compliant
C5 | Activities may be undertaken outside of the hours in condition C5 if required: (a) by the Police or a public authority for the delivery of vehicles, plant or materials; or (b) in an emergency to avoid the loss of life, damage to property or to prevent environmental harm; or (c) where the works are inaudible at the nearest sensitive receivers; or (d) where a variation is approved in advance in writing by the Planning Secretary or her nominee if appropriate justification is provided for the works. |  | RCC advised that there has been nil requirement for additional of hours work to date. Planning has commenced on the installation of the access bridge from the new development to the existing hospital, which will require extended weekend work - this will be subject to full community consultation, and will require an exemption to be sought from the DPE before works can commence RCC have maintained dialogue with adjacent properties Extended hours may also be required for water main relocation (installation of valves) in Louisiana Road (nil to date) | Compliant
C6 | Notification of such activities must be given to affected residents before undertaking the activities or as soon as is practical afterwards. | RCC advised that they letterbox dropped affected residents before bridge installation | RCC stated that this forms part of the planning process for the activity | Compliant
C7 | Rock breaking, rock hammering, sheet piling, pile driving and similar activities may only be carried out between the following hours: (a) 9am to 12pm, Monday to Friday; (b) 2pm to 5pm Monday to Friday; and (c) 9am to 12pm, Saturday. | Requirement addressed in NVMP and included in induction | RCC stated that they do not envisage having to undertake any rock hammering, sheet piling, pile driving or similar activities on the site | Compliant
Implementation of Management Plans
C8 | The Applicant must carry out the construction of the development in accordance with the most recent version of the approved CEMP (including Sub-Plans). | Management Plans are made available to Contractors as part of the onboarding process - sighted example of DECC Contract for Civil Works # 1179-DEMENV | Site induction includes key points from the CEMP and sub-plans This audit noted that site works were generally compliant with the CEMP | Compliant
Construction Traffic
C9 | All construction vehicles are to be contained wholly within the site, except if located in an approved on-street work zone, and vehicles must enter the site before stopping, unless directed by traffic control. | TCP addresses site access Authorised Traffic controller on Gate One (main access point) - sighted Statement of Completion dated 18/11/2019 | All traffic observed to be entering and leaving site in a forward motion on the day of this audit | Compliant
Hoarding / Fencing Requirements
C10 | The following hoarding requirements must be complied with: (a) no third-party advertising is permitted to be displayed on the subject hoarding/ fencing; (b) the construction site manager must be responsible for the removal of all graffiti from any construction hoardings or the like within the construction area within 48 hours of its application | Security fence installed around site with HI shade cloth covering maintained | RCC stated that where there are any areas of graffiti on the fence, the shade cloth is removed and replaced immediately There was no areas of graffiti observed during the site inspection on the day of the audit | Compliant
No Obstruction of Public Way
C11 | The public way (outside of any approved construction works zone) must not be obstructed by any materials, vehicles, refuse, skips or the like, under any circumstances. | No obstructions were noted on the day of this audit | Authorised Traffic controller on Gate One (main access point), is responsible for ensuring there is no obstruction to pedestrian movement outside Gate One No obstructions were noted on the day of this audit | Compliant
Construction Noise Limits
C12 | The development must be constructed to achieve the construction noise management levels detailed in the Interim Construction Noise Guideline (DECC, 2009). All feasible and reasonable noise mitigation measures must be implemented and any activities that could exceed the construction noise management levels must be identified and managed in accordance with the management and mitigation measures identified in the approved Construction Noise and Vibration Management Plan. | CNVM addresses requirements of the SSDA Summary of results included in Monthly Report | Noise and vibration monitors have now been removed from site as end of noisy works | Compliant
C13 | The Applicant must ensure construction vehicles (including concrete agitator trucks) do not arrive at the site or surrounding residential precincts outside of the construction hours of work outlined under condition. | Covered by general induction process, as well as the CTPMSP Sighted instruction to delivery drivers which provides detailed summary of process required to gain access | RCC stated that for major works, such as concrete pours, the WHS&E Advisor will visit the suppliers yard to conduct a project induction Vehicles not addressing protocol will be sent away | Compliant
C14 | The Applicant must implement, where practicable and without compromising the safety of construction staff or members of the public, the use of 'quackers' to ensure noise impacts on surrounding noise sensitive receivers are minimised. | Plant on site is equipment with Squawkers (quackers) |  | Compliant
Vibration Criteria
C15 | Vibration caused by construction at any residence or structure outside the site must be limited to: (a) for structural damage, the latest version of DIN 4150-3 (1992-02) Structural vibration - Effects of vibration on structures (German Institute for Standardisation, 1999); and (b) for human exposure, the acceptable vibration values set out in the Environmental Noise Management Assessing Vibration: a technical guideline (DEC, 2006) (as may be updated or replaced from time to time). | CNVM addresses requirements of the SSDA Photo 19 of Appendix D of the Independent Audit Report shows the location of the noise monitoring device | Noise and vibration monitors associated with the new development have been removed from site (end of nosy works) | Compliant
C16 | Vibratory compactors must not be used closer than 30 metres from residential buildings unless vibration monitoring confirms compliance with the vibration criteria specified in condition C20. | No residential buildings within 30 metres of site | RCC noted vibration monitor adjacent to operating theatre, with real time monitoring | Not triggered
C17 | The limits in conditions C19 and C20 apply unless otherwise outlined in a Construction Noise and Vibration Management Plan, approved as part of the CEMP required by condition B20 of this consent. |  | RCC note there has been no requirement to modify the limits in SSDA | Not triggered
Tree Protection
C18 | For the duration of the construction works: (a) street trees must not be trimmed or removed unless it forms a part of this development consent or prior written approval from Council is obtained or is required in an emergency to avoid the loss of life or damage to property; (b) all street trees must be protected at all times during construction. Any tree on the footpath, which is damaged or removed during construction due to an emergency, must be replaced, to the satisfaction of Council; (c) all trees on the site that are not approved for removal must be suitably protected during construction as per recommendations of the Tree Assessment Report prepared by Travers Bushfire & Ecology dated November 2018; and (d) if access to the area within any protective barrier is required during the works, it must be carried out under the supervision of a qualified arborist. Alternative tree protection measures must be installed, as required. The removal of tree protection measures, following completion of the works, must be carried out under the supervision of a qualified arborist and must avoid both direct mechanical injury to the structure of the tree and soil compaction within the canopy or the limit of the former protective fencing, whichever is the greater. | The following was noted during the site inspections: 1) No street trees have been trimmed or removed 2) There is no requirement to provide protection to street trees 3) Trees to be preserved on site have been marked, although there is a failure in the implementation of tree protection measures as outlined in the Tree Assessment Report dated November 2018 | With reference to the soil stockpiles in the bushfire cleared zone south of the building site, RCC should: 1) remove spoil for around tree protection zones 2) Undertake remedial works to repair root zones 3) toolbox supervisors and workers on her requirement for protection of trees | Non-Compliant
Bushfire Design
C19 | Construction of the roof, southern, eastern and western elevation(s) of the proposed works shall comply with section 3 and section 7 (BAL 29) Australian Standard AS3959-2009 Construction of buildings in bush fire-prone areas or NASH Standard (1.7.14 updated) National Standard Steel Framed Construction in Bushfire Areas – 2014 as appropriate and section A3.7 Addendum Appendix 3 of Planning for Bushfire Protection 2006. | Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) Presented letter dated 20 November 2020 from Travers Bushfire and Ecology regarding Bushfire Compliance Certification (as required by NSW RFS |  | Compliant
C20 | Construction of the northern elevation(s) of the proposed works shall comply with section 3 and section 6 (BAL 19) Australian Standard AS3959-2009 Construction of buildings in bush fire-prone areas or NASH Standard (1.7.14 updated) National Standard Steel Framed Construction in Bushfire Areas – 2014 as appropriate and section A3.7 Addendum Appendix 3 of Planning for Bush Fire Protection 2006. | Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) |  | Compliant
Air Quality
C21 | The Applicant must take all reasonable steps to minimise dust generated during all works authorised by this consent. | CEMP Section 6.1.9 provides overview of dust control measures Water cart on site to keep road surfaces damp and to spray stockpiles as required Stockpile sites tend to be reworked into site landscaping where practical to minimise disposal of material Mulch is being applied for areas of vegetation clearing | Dust monitoring has been undertaken on site Minor peaks in presented data, but compliance for reporting period Visual monitoring carried out on site, and included in weekly environmental inspections RCC stated that there has been no evidence of excessive dust being generated form the site | Compliant
C22 | During construction, the Applicant must ensure that: (a) exposed surfaces and stockpiles are suppressed by regular watering; (b) all trucks entering or leaving the site with loads have their loads covered; (c) trucks associated with the development do not track dirt onto the public road network; (d) public roads used by these trucks are kept clean; and (e) land stabilisation works are carried out progressively on site to minimise exposed surfaces. | Water cart observed on site for watering of roads and stockpiles Shaker grid maintained at exit to gate one- No trucks observed entering or leaving set without appropriate covering of loads External roads do not exhibit dirt deposition - Gateman observed using broom to remove minor spillage at Gate One | No trucks observed entering or leaving set without appropriate covering of loads Street sweeper on stand by if required Gateman observed using broom to remove minor spillage at Gate One | Compliant
Erosion and Sediment Control
C23 | All erosion and sediment control measures, must be effectively implemented and maintained at or above design capacity for the duration of the construction works and until such time as all ground disturbed by the works have been stabilised and rehabilitated so that it no longer acts as a source of sediment. | Site inspection determined control measures identified in CSWMSP Erosion Control plan have been implemented There were no observed discharges of sediment beyond the site boundary Sighted evidence of inspection of control measures | ERSED controls would appear appropriate for the site, although it was noted that there is a need to renew controls in some areas (while still effective, they are reaching the end of their serviceable limits to prevent sediment laden run off) | Compliant
Imported Soil
C24 | The Applicant must: (a) ensure that only VENM, ENM, or other material approved in writing by EPA is brought onto the site; (b) keep accurate records of the volume and type of fill to be used; and (c) make these records available to the Department or Certifying Authority upon request. |  | RCC no imported fill has been required have received road base and drainage filter material - suppliers have been requested to provide confirmation of supply source (manufactured product) | Compliant
Disposal of Seepage and Stormwater
C25 | Adequate provision must be made to collect and discharge stormwater drainage during construction of the building to the satisfaction of the Certifying Authority. Prior written approval of council must be obtained to connect or discharge site stormwater to Council's stormwater drainage system or street gutter. | S138 approval includes proposed process to dispose of stormwater . There has been no requirement to discharge of site stormwater to council drainage system |  | Compliant
Unexpected Finds Protocol - Aboriginal Heritage
C26 | In the event that surface disturbance identifies a new Aboriginal object, all works must halt in the immediate area to prevent any further impacts to the objects(s). A suitably qualified archaeologist and registered Aboriginal representatives must be contacted to determine the significance of the objects. The site is to be registered in the Aboriginal Heritage Information Management System (AHIMS) which is managed by the EESG Group and the management outcome for the site included in the information provided to AHIMS. The applicant must consult with the Aboriginal community representatives , the archaeologists and EESG Group to develop and implement management strategies for all objects/ sites. Work shall only recommence with the written approval of the EESG Group. |  | RCC advised that there have been no unexpected finds on site | Not triggered
Unexpected Finds Protocol - Historical Heritage
C27 | If any unexpected archaeological relics are uncovered during the work, then all works must cease immediately in that area and the NSW Heritage Division contacted. Depending on the possible significance of the relics, an archaeological assessment and management strategy may be required before further works can continue in that area. Works may only recommence with the written approval of the NSW Heritage Division. |  | RCC advised that there have been no unexpected finds on site | Not triggered
Waste Storage and Processing
C28 | All waste generated during construction must be secured and maintained within designated waste storage areas at all times and must not leave the site onto neighbouring public or private properties. | Waste bins observed on site were adequate for site activities |  | Compliant
C29 | All waste generated during construction must be assess, classified and managed in accordance with the Waste Classification Guidelines Part 1: Classifying Waste (EPA, 2014). | RCC have company wide initiative for waste minimisation, with a target of 80% of waste to be recycled, with a monthly waste report generated and issued to senior management - sighted report for May showing 93% achieved |  | Compliant
C30 | The Applicant must ensure that concrete waste and rinse water are not disposed of on the site and are prevented from entering any natural or artificial watercourse. | Wash out basin on site for cleanout of receiving hopper for concrete pumps and discharge chute for concrete delivery trucks - bunded and with suitable controls | Small amounts of concrete within the bund will be used on site Concrete delivery trucks required to cleanout drums at batch plant in accordance with standard industry practice Inspection of wash out areas forms part of weekly environmental checklist | Compliant
Independent Environmental Audit
C31 | Proposed independent auditors must be agreed to in writing by the Planning Secretary prior to the preparation of an Independent Audit Program or commencement of an Independent Audit. | DPE letter dated 31/10/2019 agreeing to Ken Cameron as the Independent Auditor |  | Compliant
C32 | Prior to commencement of construction, an Independent Audit Program prepared in accordance with the Independent Audit Post Approval Requirements (Department 2018) must be submitted to the Planning Secretary and the Certifying Authority. | Independent Audit Program, dated 25/11/2019, is contained on the Project Website |  | Compliant
C33 | Table 1 of the Independent Audit Post Approval Requirements (Department 2018) is amended so that the frequency of audits required in the construction phase is: (a) An initial construction Independent Audit must be undertaken within eight weeks of the notified commencement date of construction; and (b) A subsequent Independent Audit of construction must be undertaken no later than six months from the date of the initial construction Independent Audit. In all other respects Table 1 remains the same. The Planning Secretary may require the initial and subsequent Independent Audits to be undertaken at different times to those specified above, upon giving at least 4 weeks notice to the applicant of the date upon which the audit must be commenced. | Initial construction audit conducted on 15 &16 January 2020. 2nd construction audited conducted on 23 June This audit conducted on 26 November, which is within the 6 month time period |  | Compliant
C34 | Independent Audits of the development must be carried out in accordance with: (a) the Independent Audit Program submitted to the Department and the Certifying Authority under condition C32 of this consent; and (b) the requirements for an Independent Audit Methodology and Independent Audit Report in the Independent Audit Post Approval Requirements (Department 2018). | Independent audit program prepared in accordance with conditions Audit report has been developed to comply with the conditions |  | Compliant
C35 | In accordance with the specific requirements in the Independent Audit Post Approval Requirements (Department 2018), the Applicant must: (a) review and respond to each Independent Audit Report prepared under condition C32 of this consent; (b) submit the response to the Department and the Certifying Authority; and (c) make each Independent Audit Report and response to it publicly available within 60 days after submission to the Department and notify the Department and the Certifying Authority in writing at least seven days before this is done. | Previous Independent report is available on the HI Website |  | Compliant
C36 | Notwithstanding the requirements of the Independent Audit Post Approval Requirements (Department 2018), the Planning Secretary may approve a request for ongoing annual operational audits to be ceased, where it has been demonstrated to the Planning Secretary’s satisfaction that an audit has demonstrated operational compliance |  | No request has been made by RCC/HI | Not triggered
PART D PRIOR TO OCCUPATION OR COMMENCEMENT OF USE
Notification of Occupation
D1 | At least one month before commencement of operation, The date of commencement of the occupation of the development must be notified to the Planning Secretary in writing. If the operation of the development is to be staged, the Planning Secretary must be notified in writing at least one month before the commencement of each stage, of the date of commencement and the development to be carried out in that stage. |  | Project still in construction phase, scheduled to be complete by March 2021 Nil to report at the date of this schedule | Not triggered
External Walls and Cladding
D2 | Prior to the occupation of the building, the Applicant must provide the Certifying Authority with documented evidence that the products and systems used in the construction of external walls including finishes and claddings such as synthetic or aluminium composite panels comply with the requirements of the BCA. | Evidence presented of material used for cladding, with appropriate Compliance records available | Project still in construction phase Nil to report at the date of this schedule | Not triggered
D3 | The Applicant must provide a copy of the documentation given to the Certifying Authority to the Planning Secretary within seven days after the Certifying Authority accepts it. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Post-construction Dilapidation Report
D4 | Prior to occupation of the building, the Applicant must engage a suitably qualified person to prepare a post-construction dilapidation report at the completion of construction. This report is: a) to ascertain whether the construction created any structural damage to adjoining buildings or infrastructure. b) to be submitted to the Certifying Authority. In ascertaining whether adverse structural damage has occurred to adjoining buildings or infrastructure, the Certifying Authority must: i) compare the post-construction dilapidation report with the pre-construction dilapidation report required by these conditions; and ii) have written confirmation from the relevant authority that there is no adverse structural damage to their infrastructure and roads. c) to be forwarded to Council. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Protection of Public Infrastructure
D5 | Unless the Applicant and the applicable authority agree otherwise, the Applicant must: (a) repair, or pay the full costs associated with repairing, any public infrastructure that is damaged by carrying out the development; and (b) relocate, or pay the full costs associated with relocating any infrastructure that needs to be relocated as a result of the development. Note: This condition does not apply to any damage to roads caused as a result of general road usage. |  | RCC advised no infrastructure damage, or requiring relocation to date on the project Dilapidating surveys on web site will form the base line for future assessment of any damage that may have occurred | Not triggered
Utilities and Services
D6 | Prior to commencement of operation, a compliance certificate under the Section 307 of the water Management Act 2000 must be obtained from Council and submitted to the Certifying Authority. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Works as Executed Plans
D7 | Prior to occupation of the building, works-as-executed drawings signed by a registered surveyor demonstrating that the stormwater drainage and finished ground levels have been constructed as approved, must be submitted to the Certifying Authority. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Green Travel Plan
D8 | Prior to the commencement of operations, a Green Travel Plan (GTP), must be submitted to the Planning Secretary to promote the use of active and sustainable transport modes. The plan must: (a) be prepared by a suitably qualified traffic consultant in consultation with Central Coast Council and (Sydney Coordination Office) Transport for NSW; (b) include objectives and modes share targets (i.e. Site and land use specific, measurable and achievable and timeframes for implementation) to define the direction and purpose of the GTP; (c) include specific tools and actions to help achieve the objectives and mode share targets; (d) include measures to promote and support the implementation of the plan, including financial and human resource requirements, roles and responsibilities for relevant employees involved in the implementation of the GTP; and (e) include details regarding the methodology and monitoring/review program to measure the effectiveness of the objectives and mode share targets of the GTP, including the frequency of monitoring and the requirement for travel surveys to identify travel behaviours of users of the development. |  | Project still in construction phase RCC noted that Colliers/HI/LAH will be responsible - need to ensure this has been acknowledged by these parties Nil to report at the date of this schedule | Not triggered
Evacuation and Emergency Planning
D9 | Prior to the commencement of operation, a Bush Fire Emergency Management and Evacuation Plan must be prepared consistent with Development Planning – A Guide to Developing a Bush Fire Emergency Management and Evacuation Plan December 2014 and Australian Standard AS 3745 2010 Planning for Emergencies in Facilities. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Mechanical Ventilation
D10 | Prior to commencement of final operation, the Applicant must provide evidence to the satisfaction of the Certifying Authority that the installation and performance of the mechanical ventilation systems complies with: (a) AS 1668.2-2012 The use of air-conditioning in buildings – Mechanical ventilation in buildings and other relevant codes; and (b) any dispensation granted by Fire and Rescue NSW. |  | CC3 has been issued, together with supporting document from Services Consultant Will be addressed in Commissioning Phase | Not triggered
Operational Noise – Design of Mechanical Plant and Equipment
D11 | Prior to the commencement of operation, the Applicant must submit evidence to the Certifying Authority that the noise mitigation recommendations in the Wyong Hospital Redevelopment Environmental Impact Statement Report - SSD No 9536 - Acoustic and Vibration Assessment dated 31 January 2019 and prepared by Pulse Acoustic Consultancy and all reasonable and feasible noise mitigation measures have been incorporated into the design to ensure the development will not exceed the recommended operational noise levels identified in the Environmental Noise Assessment. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Road Damage
D12 | Prior to the commencement of operation, the cost of repairing any damage caused to Council or other Public Authority’s assets in the vicinity of the Subject Site as a result of construction works associated with the approved development must be met in full by the Applicant. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Fire Safety Certification
D13 | Prior to commencement of final occupation, a Fire Safety Certificate must be obtained for all the Essential Fire or Other Safety Measures forming part of this consent. A copy of the Fire Safety Certificate must be submitted to the relevant authority and Council. The Fire Safety Certificate must be prominently displayed in the building. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Structural Inspection Certificate
D14 | Prior to the commencement of occupation of the relevant parts of any new or refurbished buildings, a Structural Inspection Certificate or a Compliance Certificate must be submitted to the satisfaction of the Certifying Authority. A copy of the Certificate with an electronic set of final drawings (contact approval authority for specific electronic format) must be submitted to the approval authority and the Council after: (a) the site has been periodically inspected and the Certifying Authority is satisfied that the structural works is deemed to comply with the final design drawings; and (b) the drawings listed on the Inspection Certificate have been checked with those listed on the final Design Certificate/s. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Stormwater Quality Management Plan
D15 | Prior to the commencement of operation, an Operation and Maintenance Plan (OMP) is to be submitted to the satisfaction of the Certifying Authority along with evidence of compliance with the OMP. The OMP must ensure the proposed stormwater quality measures remain effective and contain the following: (a) maintenance schedule of all stormwater quality treatment devices; (b) record and reporting details; (c) relevant contact information; and (d) Work Health and Safety requirements. |  | Project still in construction phase Nil to report at the date of this schedule It was noted that there are no stormwater devices requiring Operation and Maintenance Planning RCC should clarify compliance requirements with DPIE regarding this approval condition | Not triggered
Warm Water Systems and Cooling Systems
D16 | The installation, operation and maintenance of water cooling systems (as defined under the Public Health Act 2010) must comply with the Public Health Act 2010, Public Health Regulation 2012 and the relevant of AS/NZS 3666.2:2011 Air handling and water systems of buildings – Microbial control – Operation and maintenance and the NSW Health Code of Practice for the Control of Legionnaires’ Disease. |  | Project still in construction phase Will be addressed during commissioning phase Nil to report at the date of this schedule | Not triggered
Outdoor Lighting
D17 | Prior to the commencement of operation, the Applicant must submit evidence from a suitably qualified practitioner to the Certifying Authority that demonstrates that installed lighting associated with the development achieves the objective of minimising light spillage to any adjoining or adjacent sensitive receivers and: (a) complies with the latest version of AS 4282-2019 - Control of the obtrusive effects of outdoor lighting (Standards Australia, 1997); and (b) has been mounted, screened and directed in such a manner that it does not create a nuisance to surrounding properties or the public road network. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Signage
D18 | Prior to the commencement of operation, way-finding signage and signage identifying the location of staff car parking must be installed. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
D19 | Prior to the commencement of operation, bicycle way-finding signage must be installed within the site to direct cyclists from footpaths to designated bicycle parking areas |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Operational Waste Management Plan
D20 | Prior to the commencement of operation, the Applicant must prepare a Waste Management Plan for the development and submit it to the Department/Certifying Authority. The Waste Management Plan must: (a) detail the type and quantity of waste to be generated during operation of the development; (b) describe the handling, storage and disposal of all waste streams generated on site, consistent with the Protection of the Environment Operations Act 1997, Protection of the Environment Operations (Waste) Regulation 2014 and the Waste Classification Guideline (Department of Environment, Climate Change and Water, 2009); (c) detail the materials to be reused or recycled, either on or off site; and (d) include the Management and Mitigation Measures included in Section 7 of the EIS. |  | Project still in construction phase RCC noted that Colliers/HI/LAH will be responsible - need to ensure this has been acknowledged by these parties Nil to report at the date of this schedule | Not triggered
Landscaping
D21 | Prior to the commencement of operation, the Applicant must prepare a Landscape Management Plan to manage the revegetation and landscaping works on-site, to the satisfaction of the Certifying Authority. The plan must: (a) detail the species to be planted on-site; (b) describe the monitoring and maintenance measures to manage revegetation and landscaping works; (c) be consistent with the Applicant’s Management and Mitigation Measures at section 7 of the EIS (d) Comply with the principles of Appendix 5 of Planning for Bush Fire Protection 2006; and (e) provide for the planting of 46 trees. |  | Project still in construction phase, currently negotiating variation to landscaping requirements Nil to report at the date of this schedule | Not triggered
D22 | The Applicant must not commence operation until the Landscape Management Plan is submitted to the Certifying Authority. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Asset Protection Zones
D23 | Prior to the commencement of operation, the development site must be managed as an inner protection zone (IPA) as outlined within section 4.1.3 and Appendix 5 of the Planning for Bush Fire Protection 2006 and the NSW RFS document Standards for asset protection zones. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
PART E POST OCCUPATION
Operation of Plant and Equipment
E1 | All plant and equipment used on site, or to monitor the performance of the development must be: (a) maintained in a proper and efficient condition; and (b) operated in a proper and efficient manner. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Operational Noise Limits
E2 | The Applicant must ensure that noise generated by operation of the development does not exceed the noise limits in the Wyong Hospital Redevelopment Environmental Impact Statement Report - SSD No 9536 - Acoustic and Vibration Assessment prepared by Pulse Acoustic Consultancy dated 31 January 2019. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
E3 | The Applicant must undertake short term noise monitoring in accordance with the Noise Policy for Industry where valid data is collected following the commencement of use of each stage of the development. The monitoring program must be carried out by an appropriately qualified person and a monitoring report must be submitted to the Planning Secretary within two months of commencement use of each stage of the development to verify that operational noise levels do not exceed the recommended noise levels for mechanical plant identified in the Wyong Hospital Redevelopment Environmental Impact Statement Report - SSD No 9536 -Acoustic and Vibration Assessment and dated 31 January 2019. Should the noise monitoring program identify any exceedance of the recommended noise levels referred to above, the Applicant is required to implement appropriate noise attenuation measures so that operational noise levels do not exceed the recommended noise levels or provide attenuation measures at the affected noise sensitive receivers. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Unobstructed Driveways and Parking Areas
E4 | All driveways, footways and parking areas must be unobstructed at all times. Driveways, footways and car spaces must not be used for the manufacture, storage or display of goods, materials, refuse, skips or any other equipment and must be used solely for vehicular and/or pedestrian access and for the parking of vehicles associated with the use of the premises. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Green Travel Plan
E5 | The Green Travel Plan required by the condition of this consent must be updated annually and implemented. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Ecologically Sustainable Development
E6 | Unless otherwise agreed by the Planning Secretary, Within six months of commencement of operation, Green Star certification must be obtained demonstrating the development achieves a minimum 4 star Green Star Design & As Built rating. If required to be obtained, evidence of the certification must be provided to the Certifying Authority and the Planning Secretary. If an alternative certification process has been agreed to by the Planning Secretary under Condition B9, Evidence of the certification must be provided to the Certifying Authority and the Planning Secretary. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Car Parking Management Strategy
E7 | The Applicant must prepare and implement a Car Parking Management Strategy within three months of the commencement of use of the Clinical Services Building, or timing otherwise agreed by the Planning Secretary. The Car Parking Management Strategy must be prepared in consultation with Council and must address, but not be limited to: (a) on-street car parking management, including details of any supporting infrastructure required for the proposed management measures; (b) measures to promote the continuing use of on-site parking by hospital users following the implementation of the paid parking on the hospital campus, including a transition period of reduced parking rates; and (c) responsibilities for the implementation and enforcement of the measures. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Outdoor Lighting
E8 | Notwithstanding Condition D17, should outdoor lighting result in any residual impacts on the amenity of surrounding sensitive receivers, the Applicant must provide mitigation measures in consultation with affected landowners to reduce the impacts to an acceptable level. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Fire Safety Certificate
E9 | The owner must submit to Council an Annual Fire Safety Statement, each 12 months after the final Safety Certificate is issued. The certificate must be on, or to the effect of, Council’s Fire Safety Statement. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Landscaping
E10 | The Applicant must maintain the landscaping and vegetation on the site in accordance with the approved Landscape Management Plan required by condition D30 for the duration of occupation of the development. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Asset Protection Zones
E11 | The asset protection zones required by condition D33 shall be maintained for the duration of occupation of the development. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Hazards and Risk
E12 | The Applicant must store all chemicals, fuels and oils used on-site in accordance with: (a) the requirements of all relevant Australian Standards; and (b) the NSW EPA’s Storing and Handling of Liquids: Environmental Protection – Participants Manual’ if the chemicals are liquids. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
E13 | In the event of an inconsistency between the requirements of condition E12(a) and E12(b), the most stringent requirement must prevail to the extent of the inconsistency. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Dangerous Goods
E14 | Dangerous goods, as defined by the Australian Dangerous Goods Code, must be stored and handled strictly in accordance with: (a) all relevant Australian Standards; (b) for liquids, a minimum bund volume requirement of 110% of the volume of the largest single stored volume within the bund; and (c) the Environment Protection Manual for Authorised Officers: Bunding and Spill Management – technical bulletin (EPA, 1997). |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
E15 | In the event of an inconsistency between the requirements E14(a) to E14(c), the most stringent requirement must prevail to the extent of the inconsistency. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
E16 | The new access road connecting the hospital site to Louisiana Road is restricted to emergency and service vehicles only. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
ADVISORY NOTES
AN1 | All licences, permits, approvals and consents as required by law must be obtained and maintained as required for the development. No condition of this consent removes any obligation to obtain, renew or comply with such licences, permits, approvals and consents. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Long Service Levy
AN2 | For work costing $25,000 or more, a Long Service Levy must be paid. For further information please contact the Long Service Payments Corporation Helpline on 131 441. | Presented evidence of payment of levy (October 2020) |  | Compliant
Legal Notices
AN3 | Any advice or notice to the consent authority must be served on the Planning Secretary |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Access for People with Disabilities
AN4 | The works that are the subject of this application must be designed and constructed to provide access and facilities for people with a disability in accordance with the BCA. Prior to the commencement of above ground works, the Certifying Authority must ensure that evidence of compliance with this condition from an appropriately qualified person is provided and that the requirements are referenced on any certified plans. | Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) notes Draft Disability access report dated February 2020 prepared by Cheung Access | CC3 will include final report - currently issued with clarification | Compliant
Utilities and Services
AN5 | Prior to the construction of any utility works associated with the development, the Applicant must obtain relevant approvals from service providers | Electricity: L3 Design Report dated 20/12/2019 (LEHR) - Sighted Ausgrid Approval of design dated 6/01/2020 Presented Amendment 2 for Ausgrid Certificate dated 27/04/2020 Stormwater: S138 Certificate issued | Gas: use exiting facility connection - no additional connection required | Compliant
AN6 | Prior to the commencement of above ground works written advice must be obtained from the electricity supply authority, an approved telecommunications carrier and an approved gas carrier (where relevant) stating that satisfactory arrangements have been made to ensure provisions of adequate services. | Crown Certificates No CRO-20015 (CC2) dated 25/03/2020 Certifier: Blackett Maguire + Goldsmith - David Blackett (Accreditation No BPB0032) includes design statements covering electrical and mechanical works Presented evidence of signed agreement with Jemena for update of gas meter |  | Compliant
Road Design and Traffic Facilities
AN7 | All roads and traffic facilities must be designed to meet the requirements of Council or RMS (whichever is applicable). The necessary permits and approvals from the relevant road authority must be obtained prior to the commencement of road or pavement construction works. | Sighted approval as noted above | RCC advised no change at the time of this audit | Compliant
Road Occupancy Licence
AN8 | A Road Occupancy Licence must be obtained from the relevant road authority for any works that impact on traffic flows during construction activities. |  | RCC stated a Road Occupancy Licence not required - not identified in CTPMSP | Not triggered
SafeWork Requirements
AN9 | To protect the safety of work personnel and the public, the work site must be adequately secured to prevent access by unauthorised personnel, and work must be conducted at all times in accordance with relevant SafeWork requirements. | Site fencing established - was in good order during site inspection Full time gateman/traffic controller at Gate 1 (Main construction access point) | RCC have established controlled access gate for personnel to enter construction site RCC note fully compliant /Certified WHS system being implemented on site (not subject to detailed review during this audit)Process addressed in Induction | Compliant
Hoarding / Fencing Requirements
AN10 | (a) the Applicant must submit a hoarding application to Council for the installation of any hoardings over Council footways or road reserve. |  | No hoardings required over Council footways or road reserve Jersey Curb barriers erected on Louisiana Road for protection of pedestrians with the agreement of Council | Compliant
Handling of Asbestos
AN11 | The Applicant is to consult with SafeWork NSW concerning the handling of any asbestos waste that may be encountered during construction. The requirements of the Protection of the Environment Operations (Waste) Regulation 2014 with particular reference to Part 7 – ‘Transportation and management of asbestos waste’ must also be complied with. | Presented evidence of identification of asbestos and requirements for safe removal | Process defined in unexpected finds procedure | Compliant
Fire Safety Certificate
AN12 | The owner must submit to Council an Annual Fire Safety Statement, each 12 months after the final Safety Certificate is issued. The certificate must be on, or to the effect of, Council’s Fire Safety Statement. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered
Roadworks and Access
AN13 | Prior to any further development on the hospital site beyond this consent, a post operational intersection analysis report should be undertaken and referred to TfNSW(RMS) for consultation. The report should include: (a) a review of the traffic conditions and the level of service of the intersection of the Pacific Highway / Craigie Avenue / Hospital Entrance. (b) any potential intersection improvements required to meet future demand of the hospital. |  | Project still in construction phase Nil to report at the date of this schedule | Not triggered